## How to use
Change Control Form
Purpose | Take a change from proposal to verified closure with the assessments regulators expect - ICH Q10's change management element, EU GMP Annex 15 §11, and the QMSR/ISO 13485 change requirements all look for impact assessment BEFORE approval and verification of effectiveness AFTER implementation.
How to use | One workbook per change (file it by change ID). Work the steps top to bottom - PROPOSE, ASSESS, APPROVE, IMPLEMENT, CLOSE. The worked example row shows the expected level of detail.
Step / question | The change-control step. Do not skip rows - record N/A with a reason instead.
Response / detail | What was proposed, assessed or decided - specific enough to reconstruct the decision.
Evidence / reference | Where the proof lives: assessment IDs, updated document numbers, training records.
Status | Open / In progress / Complete / N-A via the dropdown.
Template version | v1.0 (2026-08) - record this reference on the completed record so the revision used is traceable.
About | This template is a working aid from Complere (complere.tech). It does not by itself make any record or organisation compliant - adapt it to your own procedures and approve it through your own document control.
See it live | See how Complere covers this in one governed, inspection-ready workflow - request a demo at complere.tech/request-demo
(c) 2026 Complere - complere.tech

## Change Control
Change Control Form
Impact-assessed, approved, verified. Worked example in row 5 (italic) - replace with your own change.
Step / question | Response / detail | Evidence / reference | Owner | Date | Status
PROPOSE - Describe the change (current state, proposed state, affected systems/documents) | Increase mixing time 10->12 min on line 2 product X; affects MFR-102 and SOP-210 | CC-2026-041 | Prod. Engineer | 2026-05-10 | Complete
PROPOSE - Describe the change (current state, proposed state, affected systems/documents)
PROPOSE - Rationale: why is the change needed (data, deviation, improvement, regulation)
PROPOSE - Classification (major / minor) with rationale
ASSESS - Product quality impact (specifications, stability, validated state)
ASSESS - Validation impact: is re-validation or additional qualification required?
ASSESS - Regulatory impact: filing variation, notification, or none - with rationale
ASSESS - Documents affected: list every SOP, MFR, specification to be revised
ASSESS - Training impact: who must be (re)trained before go-live
APPROVE - QA and process-owner approval BEFORE implementation; conditions recorded
IMPLEMENT - Actions executed per plan; document revisions issued through document control
IMPLEMENT - Training completed and recorded before the change is used
CLOSE - Post-implementation review: did the change achieve its purpose without adverse effect?
CLOSE - Effectiveness evidence examined (first batches, monitoring data) and conclusion recorded
CLOSE - QA closure sign-off; record retrievable under the change ID
(c) 2026 Complere - complere.tech - see how Complere covers this in a governed, inspection-ready workflow: complere.tech/request-demo