## Instructions
FDA QMSR Transition Checklist
Instructions - read before use
Purpose | Track the work of moving a Part 820 (QSR-era) quality system to the QMSR (effective 2026-02-02): ISO 13485:2016 incorporated by reference plus FDA additions at 820.35 (records) and 820.45 (labeling/packaging). Companion to complere.tech/compliance/fda-qmsr/.
How to use | Work phase by phase. Every line needs an owner, a status, and - when complete - the evidence reference that proves it (document ID, change record, audit report). Run the document updates under change control so the transition itself leaves an inspectable trail.
Field guidance
Phase / task | Transition activity. Add rows for site-specific work.
Owner | Accountable person.
Status | Not started / In progress / Complete / N/A.
Evidence / record ref | Where the proof lives once done.
Notes | Decisions, blockers, scope notes.
This template is a working aid from Complere (complere.tech). It does not by itself make any record or organization compliant - adapt it to your own QMS procedures and have QA approve the adapted version.

## Transition Checklist
FDA QMSR Transition Checklist
Worked example in row 5 (italic) - replace with your own records.
Phase / task | Owner | Status | Evidence / record ref | Notes
1 GAP ASSESSMENT - Map each legacy procedure to its ISO 13485:2016 clause + FDA additions | QA Mgr | In progress | GAP-LOG-001 | 21 of 64 procedures mapped
1 GAP ASSESSMENT - Map each legacy procedure to its ISO 13485:2016 clause + FDA additions (820.35, 820.45)
1 GAP ASSESSMENT - Identify procedures with terminology tied to the old QSR vocabulary
1 GAP ASSESSMENT - Confirm risk-based thinking is visible across QMS processes (per ISO 13485)
1 GAP ASSESSMENT - Record the gap list as the transition backlog with priorities
2 DOCUMENT UPDATES - Open change record(s) covering the documentation update wave
2 DOCUMENT UPDATES - Update quality manual / top-level docs to QMSR + ISO 13485 references
2 DOCUMENT UPDATES - Update affected SOPs, forms, and templates; retire superseded revisions
2 DOCUMENT UPDATES - Verify records procedures meet 820.35 (incl. signature and date expectations)
2 DOCUMENT UPDATES - Verify labeling and packaging controls meet 820.45
3 MANAGEMENT REVIEW - Confirm cadence, inputs, and minutes meet ISO 13485 5.6 - as producible records
3 MANAGEMENT REVIEW - Brief leadership: management review records are now reviewable in FDA inspections
4 INTERNAL AUDIT - Re-point audit program/checklists at ISO 13485 clauses + FDA additions
4 INTERNAL AUDIT - Schedule a transition-verification audit; treat findings via CAPA
4 INTERNAL AUDIT - Brief auditors: internal & supplier audit records are now reviewable in FDA inspections
5 TRAINING - Assign training on every revised procedure before the old revision retires
5 TRAINING - Capture completion evidence tied to the new revisions; verify competency where required
6 READINESS - Run a retrieval drill: management review record, internal audit file, CAPA chain - timed
6 READINESS - Review supplier controls and quality agreements against ISO 13485 7.4 expectations
6 READINESS - Familiarize the team with the CP 7382.850 inspection structure (six QMS areas)