## How to use
Validation Master Plan Template
Purpose | Draft a Validation Master Plan section by section - the planning document EU GMP Annex 15 expects and GAMP 5 structures: what is validated, on what risk basis, by whom, to what acceptance standard, on what schedule.
How to use | Each row is a VMP section: the middle column says what the section must cover; write your content (or the reference to where it lives) in the third, assign an owner, and track drafting status. The completed grid IS your VMP skeleton - transfer to your controlled document template for approval.
VMP section | The section of the plan.
What this section must cover | The content Annex 15 / GAMP 5 expect to find there.
Your content / reference | Draft text or a pointer to the controlled document that holds it.
Status | Draft / In review / Approved / N-A via the dropdown.
Template version | v1.0 (2026-08) - record this reference on the completed record so the revision used is traceable.
About | This template is a working aid from Complere (complere.tech). It does not by itself make any record or organisation compliant - adapt it to your own procedures and approve it through your own document control.
See it live | See how Complere covers this in one governed, inspection-ready workflow - request a demo at complere.tech/request-demo
(c) 2026 Complere - complere.tech

## VMP Builder
Validation Master Plan Template
Section-by-section per EU GMP Annex 15 §2 / GAMP 5. Worked example in row 5 (italic).
# | VMP section | What this section must cover | Your content / reference | Owner | Status
e.g. | Validation policy | The organisation's intent and commitment: what gets validated and the standard applied | QP-001 §4 quality policy statement, referenced | Val. Manager | Approved
1 | Purpose & scope | Sites, systems, processes and utilities the plan covers - and what it explicitly excludes
2 | Validation policy | The organisation's validation intent and the regulatory basis (Annex 15, GAMP 5, QMSR as applicable)
3 | Organisation & responsibilities | Named roles: who authors, reviews, approves and executes validation work
4 | System / process inventory | How the validation inventory is maintained and where it lives
5 | Risk-based approach | How risk assessment determines validation depth (GAMP categories, impact assessment)
6 | Documentation standards | The document set per validation (URS, RA, IQ/OQ/PQ or CSA-based) and templates used
7 | Acceptance criteria philosophy | How acceptance criteria are set and what happens on failure
8 | Change & deviation handling | How changes and deviations DURING validation are controlled and recorded
9 | Periodic review & revalidation | Triggers and frequency for maintaining the validated state
10 | Schedule & priorities | The plan: order of work, target dates, resource assumptions
11 | References | Governing SOPs, standards and regulations referenced by this plan
(c) 2026 Complere - complere.tech - see how Complere covers this in a governed, inspection-ready workflow: complere.tech/request-demo